## Overview
overview of project work
a. | the roles and responsibilities of the team members
b. | the project requirements
c. | the data requirements
d. | the way you will run your project
e. | the tools you will use for the technical work
f. | the tools you will need for the running of your team
g. | the deliverables of your work
You will use some of the above decision content in the deliverables outlined next.
Data Description
a. | House listings: detailed house listings data including full house descriptions and average review scores
b. | Rental calendar: detailed rental calendar data for house listings, including listing id, rental price and availability for each calendar day
c. | Customer reviews: detailed review data for house listings including a unique id for each reviewer and their detailed comments for the property
Problem Definition and Business Intelligence Scope
D01 | Problem and proposed solution overview | use any kind of tools, reporting style and diagramming techniques
D02 | Analysis of the problems and needs that will be covered with the
D03 | Team organization, tasks identified and project timeline
System Design & Development
D04 | List of development and collaboration tools used | 1. Create a staging environment for the necessary data 2. Define, design and implement the necessary Extract, Transform, Load (ETL) tasks 3. Design and implement a data warehouse and necessary data marts (if needed) 4. Define and implement necessary Information Visualization & Data Analytics and Dashboards 5. Discuss the implemented Business Reports and corresponding findings
D05 | BI system overview, architecture & system workflow/workflows
D06 | Database diagrams and source code (OLTP, Staging, DW, DMs)
D07 | Data flow diagram/diagrams & transformations explanations
D08 | Code files used for data processing
D09 | Data Visualization platform’s (e.g. from Power BI) files, relevant
Data Visualization & Advanced Analytics
D10 | A description and presentation of the analytics along with the source code | a. Which are the company’s top priced properties b. Which are the company’s top rated properties c. Which hosts are the busiest? | A secondary objective is to build a machine learning model that predicts the price of a listing depending on its attributes (e.g. number of bedrooms, property type, etc.). This model will be used for suggesting the price that a new listing should take. Then you should use this house-price model to answer the following questions: d. Which attributes are the most critical to the price of a listing? e. Which listings are the most undervalued? f. Which listings are the most overvalued? g. Identify candidates based on their value and ratings whose hosts could be notified for increasing their price.
D11 | Project Evaluation, advantages, limitations and suggestions for future

## Timetable
# | D# | Task | Start Date | End Date | Vasilis | Ilias | Klevis | Maria | Stavros
1 | D03 | Propose a task management system for task tracking | 2020-12-06 | 2020-12-07 | X | X | X | X | X
| D03 | Combine proposed solutions and create the final task tracking tool | 2020-12-07 | 2020-12-07 |  |  |  | X
| D01 | Initial high-level description of project scenario, the business needs and the proposed solution. Write first deliverable draft. | 2020-12-06 | 2020-12-07 |  | X
| D02 | Describe in more detail what we are asked to answer and the proposed BI solution to achieve the desired results. Here, we get more specific compared to D01. | 2020-12-06 | 2020-12-07 |  | X
| D06 | Initial inspection of OLTP tables and csv data files -> understand the given data | 2020-12-06 | 2020-12-07 | X |  | X |  | X
| D05 | Defining the data we need from the OLTP system to build our BI system and answer the questions at hand | 2020-12-07 | 2020-12-08 | X | X | X | X | X
| D05 | Data Warehouse schema selection and fact/dimension Tables selection based on business needs | 2020-12-08 | 2020-12-10 | X | X | X | X | X
| D05 | Staging enviroment definition based on desired Data Warehouse design | 2020-12-08 | 2020-12-09 | X | X | X | X | X
| D05 | Define data constraints for Fact and Dimension Tables of the DW and set foreign keys | 2020-12-09 | 2020-12-11 | X | X | X | X | X
| D06 | Create Staging area (DB) with SQL from OLTP | 2020-12-09 | 2020-12-11 |  |  |  |  | X
| D06 | Create an initial .sql file for transformation of OLTP to Staging DB | 2020-12-11 | 2020-12-11 | X | X | X | X | X
| D09 | Power BI dashboard creation and investigation | 2020-12-11 | 2020-12-13 |  | X
| D06 | Create an initial .sql file for transformation of Staging DB to Data Warehouse | 2020-12-12 | 2020-12-12 | X | X | X | X | X
| D06 | Transform data data from Staging to DW | 2020-12-12 | 2020-12-14 | X |  |  |  | X
| D08 | Define initial selection of features/attributes to be used in our ML model | 2020-12-12 | 2020-12-13 | X | X | X | X | X
| D10 | Extract required features and data from DW for ML preprocessing | 2020-12-13 | 2020-12-13 | X
| D10 | ML preprocessing over OLTP / DW data | 2020-12-13 | 2020-12-15 |  |  | X | X
| D06 | Build DW Views and extract csv files for ML processing | 2020-12-13 | 2020-12-14 | X
| D06 | Data Marts creation | 2020-12-14 | 2020-12-14 |  |  |  |  | X
|  | First version of a presentation of our overall BI system design/architecture | 2020-12-14 | 2020-12-15 |  |  |  |  | X
|  | Final project presentation structure created to populate with data | 2020-12-15 | 2020-12-15 | X
| D01 | Proofreading, updating and submitting D01, D02, D03 deliverables | 2020-12-15 | 2020-12-15 | X | X
| D10 | Machile learning model, compare different regression methods metrics | 2020-12-15 |  |  |  | X | X
| D04 | D04 deliverable on development and collaboration tools | 2020-12-15 | 2020-12-15 | X | X
|  | StayMore logo creation | 2020-12-15 | 2020-12-15 | X
|  | Draw.io/app.diagrams.net PowerBI System and Dara Warehouse Database Design | 2020-12-15 | 2020-12-15 |  |  |  |  | X
| D08 | Investigate algorithms for classification method instead of standard regression techniques | 2020-12-16 | 2020-12-17 |  |  |  | X
| D09 | PowerBI busiest hosts dashboard | 2020-12-16 | 2020-12-17 | X
| D09 | PowerBI top rated properties | 2020-12-16 | 2020-12-17 |  |  |  |  | X
| D05 | Finalizing files & presentation to submit for BI system overview, architecture & system workflow/workflow | 2020-12-16 | 2020-12-19 | X |  |  |  | X
| D06 | Finalizing files & presetantion to submit for Database diagrams and source code (OLTP, Staging, DW, DMs) | 2020-12-16 | 2020-12-19 | X |  |  |  | X
| D07 | Finalizing files & presnetation to submit for Data flow diagram/diagrams & transformations explanation | 2020-12-16 | 2020-12-19 | X |  |  |  | X
Visualization & Data Analyticsand Dashboards
Discuss the implemented Business Reportsand corresponding findings
Analytic calculations and visualizations
Machine learning model
Prepare an evaluation of your resulting system
Submit the project portfolio
Presentation
| # | Deliverables | Completed
| D01 | Analysis of the problem/ proposed BI solution | X
| D02 | Problem and proposed solution overview | X
| D03 | Team organization, tasks identified and project timeline | X
| D04 | List of development and collaboration tools used | X
| D05 | BI system overview, architecture & system workflow/workflow | X
| D06 | Database diagrams and source code (OLTP, Staging, DW, DMs) | X
| D07 | Data flow diagram/diagrams & transformations explanation | X
| D08 | Code files used for data processing
| D09 | Data Visualization platform’s (e.g. from Power BI) files, relevant screenshots and description of functionality and intended usage and purpose
| D10 | A description and presentation of the analytics along with the source code and other necessary files (ML)
| D11 | Project Evaluation, advantages, limitations and suggestions for future steps
Note on E43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A series of analytics can provide answers to questions like: a.Which are the company’s top priced properties b.Which are the company’s top rated properties c.Which hosts are the busiest?

## Gantt Chart
The BI Project Gantt Chart
|  | weeks | 1 | [7 empty] | 2 | [7 empty] | 3
Deliverables | Start Date | End Date | 2020-12-05 | 2020-12-06 | 2020-12-07 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11 | 2020-12-12 | 2020-12-13 | 2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 2020-12-20 | 2020-12-21 | 2020-12-22
Problem and proposed solution overview | 2020-12-06 | 2020-12-07
Analysis of the problem/ proposed BI solution | 2020-12-06 | 2020-12-07
Presentation